## Sheet1
Week of | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Notes
2023-09-11 | [5 empty] | 1 hour team meeting |  | First week, not much done because we had no plan
2023-09-18 |  |  |  |  | Group meeting With sponsor |  |  | Second week, got plan set up and met with sponsor
2023-09-25 | [5 empty] | 2 hr looking through various ways for our arduino to talk to Nodered |  | Very slow week, mostly just communicating with sponsor about specifics for the project
2023-10-02 | 2 hr setting up personal arduino to read in temperature and humidity data |  | 1 hour group meeting | 3 hours developing UDP system to talk to Nodered with arduino | 2 hours attempting to set up MQTT, 30 min for hardware drop | 3 hours for my section on the project charter |  | Big week for work on this project, as I had more time for it than usual
2023-10-09 |  |  |  | 2 hours trying to port work over to MQTT, no luck still. | 1 hour meeting with group for project charter |  |  | I kept working on MQTT but it goes over my head quite a bit, am planning on finding a day after midterms to just learn as much as i can
2023-10-16 |  |  |  |  | 1 hour meeting with sponsor |  |  | Midterm week, Homework picked up so not much got done on my end
2023-10-23 | 1 hour work on status report |  | 1 hour meeting with TA | 2 hour work on midterm for class | 1 hour meeting with sponsor |  |  | Same as last week, midterms and homework were keeping me from doing much
2023-10-30 |  |  | 1 hour meeting on discord | 1 hour on (late) weekly status report (sorry!) |  | 2 hours on attempting non-local communication with html and arduino |  | A sort of off week, i attempted other routes of communication cause I cant tell if MQTT is possible here
2023-11-06 |  |  |  |  | 1 hour meeting with team, broke off into seperate groups |  |  | Birthday week and a lot of assignments piling up, did not get as much done as I wanted.
2023-11-13 |  |  | 2 hour working on connecting R4 to wifi |  | 1 hour meeting with team |  | 4 hours studying mqtt | Right before fall break so had to take time for assignments, but was able to study mqtt!
2023-11-20 | [5 empty] | 2 hours on mqtt, setting up personal server and trying to get it to connect |  | Fall break, no meetings but did work on trying to figure out mqtt
2023-11-27 |  | 3 hour work on setting up local MQTT broker for testing | 1 hour learning how to use the given shield |  | 1 hour using the shield to read in the needed data | 1 hour meeting with sponsor |  | most of the planning feels done at this point, and it feels like the application stage should be soon
2023-12-04 | 1 hour on structure for data packets from station |  |  | 1 hour meeting with TA for end of semester |  | 1 hour meeting with sponsor | 3 hours for final | the system seems to not be talking to MQTT at all, but Jeffrey has a connection so i think it might be solved.
2023-12-11 |  |  | 1 hour group meeting | 2 hours presentation and timesheet logging | 2 hour recording for presentation |  |  | last week! mostly working on assignments.