## Sheet1
Week 4 (Sept. 17-23)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 1 | Group meeting - no spons. | -Some entries frm prior weeks. -First meeting with sponsor, first considerable week. -Established tenative availability, meeting schedule
Team Meeting 2 | 1.5 | Group
Team Meeting 3 | 1.5 | Sponsor
Research - Node-Red | 2
Research - MQTT | 1
Misc Prep | 3
Week 5 (Sept. 24-30)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 0.5 |  | -node-red initial deployment. Insecure, need to get certs
Team Meeting 2 | 1 | remote too
node-red Deployment | 2 | temporary implementation
Week 6 (Oct. 1-07)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 0.5 |  | -new hardware, will propogate to team asap -hardware w/o wireless connectivity? clarify intent -devboards incompatible with sensor daughterboards?
Team Meeting 2 | 1 | 1st hardware drop
MQTT Broker setup | 2 | insecure
Research TLS certs | 1
Week 7 (Oct. 8-14)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 0.5 |  | -finally secured web-facing applications, long overdue -MQTT is being finnicky, but now works on all interfaces
Team Meeting 2 | 1
Apache Server | 2
TLS Certs | 0.5
MQTTS | 5 | dear god
Week 8 (Oct. 15-21)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 1 | long, unproductive :( | -no updates
Team Meeting 2 | 1
Week 9 (Oct. 22-28)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 0.5 |  | -finally got hardware out to team -demos coming soon?
Team Meeting 2 | 1
midterm | 1
hardware dropoff | 0.5
"blinky" demo over http | 1
Payload schema | 0.5 | WIP
Week 10 (Oct. 29 - Nov. 4)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 0.5 |  | -added insecure mqtt option as group is struggling to connect -connection works fine for me, on and off network? -looks like pgAdmin works differently than expected. Will have to manually configure everyone's profile. ugh.
Team Meeting 2 | 1
demo MQTT connect | 2
MQTT insecure | 0.5 | temporary
Ingest pipeline rev. 1 | 1 | temp testing
Design DB schema | 0.5
Spin up DB | 2
Week 11 (Nov. 5-11)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 0.5 |  | -started move towards containerization. More secure, and easier to manage. Node-red not yet transitioned, as I dont want to mount /etc/letsencrypt -possibly move away from current mount structure? I don't wanna lol. It's organized. -Everyone should have proper accounts and privs this time. For real real.
Team Meeting 2 | 1
containerization | 3 | incomplete
node-red accounts | 1
pgAdmin config | 1
MQTT runthrough | 0.5
Milestone Planning Session | 1
Week 12 (Nov. 12-18)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 0.5 |  | -out with the flu, attended meetings remotely
Team Meeting 2 | 0.5
Week 13 (Nov. 19-25) THANKSGIVING
Week 14 (Nov. 26 - Dec. 2)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 0.5 |  | -dashboards should be kept to node-red where possbile per Joe. -there are a few plugins that look promising, but low pull ct? -is this an Enock thing? Dylan? Front end.
Team Meeting 2 | 1
Trello tasks | 0.5
Endpoint design | 0.5
Research CBOR | 0.5 | existing node widget?
Research node webcontent | 0.5
Week 15 (Dec. 3-9)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 0.5 |  | -cert renewal is annyoing. have to spin down webserver, as certbot needs port 80. Automate monthly in middle of night? -desperately need to write systemd service to automatically run startup scripts. Lord knows how long node-red was dead.
Team Meeting 2 | 1
Renew Certs | 0.5 | Automate?
Arduino JSON lib | 1 | Annoying. CBOR?
Update pgAdmin, node-red | 0.5
server outage fix | 0.5 | no clear cause, reboot?
Week 15 (Dec. 10-16)
Task | Time (approx) | Notes | Overview
Team Meeting 1 | 0.5 |  | -David provided team with direct actions to take moving into next semester. relayed to team. -Much improved team comms and productivity. -Since getting Trello board up-to-date, state of project is looking healhty
Team Meeting 2 | 1
Final Paper | 2
week 15 progress update | 0.5
project plan | 0.5
Summary Video/ meeting | 1
Misc. Cleanup | 1