## Weekly Summary
Week of | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Notes
Week 2 | [7 empty] | Quiet week… still waiting for class instructions and project team to meet after break.
Week 3 |  |  |  |  | Meeting with sponsor |  |  | Meetings were established for the new semester, but progress was slow due to initial stages.
Week 4 |  |  | Meeting with TA | Prepare for API design |  | Prepare for API design |  | Sponsor meetings initiated discussions on component delivery; focus shifted to API design and expo planning, with concerns over prototype deadlines.
Week 5 |  | Implement GPS code | Implement GPS code |  | Meeting with sponsor |  |  | Components acquired and initial code set up for data sensing and internet connection
Week 6 |  |  | Meeting with TA | Implement CBOR encoding |  |  |  | Next steps include database integration and API development, but concerns persist about meeting prototype deadlines and scheduling changes.
Week 7 |  |  |  |  | Meeting with sponsor |  |  | Meetings were changed and smaller teams were formed as a solution to schelduing conflicts.
Week 8 |  |  | Meeting with TA, Complete CBOR integration |  | Integrate CBOR serialization |  |  | Successful implementation of CBOR encoding in the system; next steps involve finalizing integration with the database and optimizing API endpoints, anticipating challenges with data volume and cross-platform compatibility.
Week 9 |  |  |  |  | Meeting with sponsor |  |  | Continued integration of CBOR serialization for data transmission; focus now on refining the implementation to meet industry standards and best practices, with challenges in handling nested data structures and legacy systems compatibility.
Week 9 |  |  | Meeting with TA, Node-Red Dashboard POC | Embedded progress |  |  |  | Continued integration of CBOR serialization for data transmission; focus now on refining the implementation to meet industry standards and best practices, with challenges in handling nested data structures and legacy systems compatibility.
Week 9 |  |  |  |  | Meeting with sponsor | Backend improvements |  | Completion of CBOR integration in communication protocols; upcoming tasks include stress testing for scalability and performance optimization, aiming to minimize computational overhead.
Week 10 |  |  | Meeting with TA |  | Develop frontend interface |  |  | Progress with a Node-Red Dashboard proof-of-concept and backend improvements; key focus on integration of project components, documentation production, and project value proposition refinement.
Week 11 | Implement location history display |  |  |  | Meeting with sponsor |  |  | Significant advancement in frontend interface development; next steps include integrating interactive maps and data visualization tools while addressing challenges with cross-browser compatibility.
Week 12 | Finalize UI |  | Meeting with TA |  | Implement location history display |  |  | Successful implementation of location history data display; upcoming work involves implementing data filtering and analysis features, with a focus on data privacy and security.
Week 12 | Configure data flow |  | Finalize UI | Finalize UI | Meeting with sponsor |  |  | Final UI adjustments and preparation for live data influx into the SQL database; concerns raised about potential issues with real data flow.
Week 13 | Improve UI |  | Meeting with TA |  |  |  | Configure data flow | Poster completion and successful data pipeline setup; ongoing focus on UI enhancements and device connectivity to ensure presentation readiness.
Week 13 | Ensure device connectivity |  |  |  | Meeting with sponsor |  |  | Establishment of comprehensive quality assurance processes; next steps involve rigorous testing to identify and resolve remaining issues or bugs, particularly focusing on system reliability and performance.
Week 14 |  |  | Meeting with TA |  |  | Establish QA process | Ensure device connectivity | Completion of initial testing phase; upcoming priority is user acceptance testing to gather feedback and refine the user experience based on stakeholders' inputs.
Week 14 | Establish QA process | Complete initial testing phase | Establish QA process | Conduct rigorous testing | Meeting with sponsor | EXPOOOOO
Week 15 |  |  | Meeting with TA,Meeting with sponsor